## can you add more details. assum
Aspect | Description | Example
Core Values | * Agility * Collaboration * Transparency * Quality | *We will release new features in bi-weekly sprints to adapt to market changes quickly. * Developers and UI/UX designers will collaborate on daily stand-up meetings to ensure a seamless user experience. * A shared project management tool will provide real-time progress updates for all stakeholders. * Code reviews will be mandatory before every code commit to maintain high coding standards.
Project Management | * Project management tool (e.g., Jira) * Regular stand-up meetings * Backlog prioritization | * We will use Jira to track user stories, bugs, and tasks. * Stand-up meetings will be held every morning for 15 minutes to discuss progress and roadblocks. * User stories will be prioritized based on user feedback, market trends, and business impact.
Development Methodology | * Agile methodology (e.g., Scrum) with 2-week sprints * User story definition and prioritization * Daily code reviews | * We will adopt the Scrum methodology with 2-week sprints to deliver working functionalities incrementally. * User stories will be clearly defined using the INVEST framework (Independent, Negotiable, Valuable, Estimatable, Sized, Testable) for better prioritization. * Developers will conduct code reviews daily to identify and fix bugs early in the development process.
Version Control | * Version control system (e.g., Git) | * We will use Git to track code changes, collaborate on features, and revert to previous versions if necessary. * A branching strategy will be implemented to isolate development work on new features.
Testing | * Unit testing * Integration testing * User Acceptance Testing (UAT) * Penetration testing | * Developers will write unit tests to ensure individual code components function correctly for stock quotes, order placement, and account management. * Integration testing will verify how different parts of the application, such as the trading engine and user interface, work together seamlessly. * UAT will involve real users testing the application's functionality and providing feedback before launch. * Penetration testing will be conducted by a security expert to identify and address any vulnerabilities in the system.
Communication | * Regular communication channels (stand-up meetings, team chats, progress reports) * Communication plan for stakeholders (Product Owner, Business Analysts) | * Daily stand-up meetings will be held to discuss progress and roadblocks. * A dedicated Slack channel will be used for real-time communication and collaboration among team members. * Weekly progress reports will be shared with the Product Owner and Business Analysts to ensure alignment with project goals.
CI/CD | * Automation of build, test, and deployment process | * We will utilize a CI/CD pipeline to automate the process of building, testing, and deploying the application to the staging environment after every code commit. * Manual approval will be required before deploying the application to the production environment.
Documentation | * Clear and concise documentation for code, functionalities, and user stories | * Developers will use code comments and API documentation tools like Swagger to document their code. * User stories will be documented in Jira with detailed acceptance criteria. * A functional requirements document will be created to outline the overall functionalities of the application.
Benefits | * Increased project efficiency * Improved quality * Enhanced team collaboration * Faster adaptation to change | * By releasing new features frequently, we can gather user feedback early and iterate quickly. * Automated testing and code reviews will minimize bugs and ensure a high-quality application. * Regular communication and collaboration will foster a positive work environment and efficient problem-solving. * The Agile methodology allows us to adapt to changing market conditions and user needs rapidly.